## 01 GOAL SETTING
STAGE 3: REVERSE OUTCOME MODELING - GOAL SETTING
Define your institutional health target and feasibility parameters
CURRENT STATE BASELINE
Current Overall Health Index: | [ENTER: e.g., 72]
Assessment Date: | [ENTER: Date]
TARGET DEFINITION
Target Overall Health Index: | [ENTER: e.g., 80] | (0-100, recommend 75-85 for realistic targets)
Target Achievement Timeline: | [ENTER: months, e.g., 12] | (Typical: 6-24 months)
IMPROVEMENT PARAMETERS
Available Budget (₹): | [ENTER: Budget]
Priority Focus Areas: | [SELECT: Strategic focus] | (Academic / Facilities / Staff / Holistic)
Risk Tolerance: | [SELECT: Low / Medium / High]
QUICK GAP ANALYSIS
Gap to Target (Target - Current): | FORMULA | If 80 - 72 = 8 points needed
Average Improvement per Dimension: | FORMULA | 8 / 14 dimensions ≈ 0.57 per dimension
% Improvement Needed: | FORMULA | (8 / 72) × 100 = 11.1%
FEASIBILITY ASSESSMENT
Quick Assessment:
If gap ≤ 5 points and timeline ≥ 12 months: | HIGHLY FEASIBLE
If gap 5-10 points and timeline 12-18 months: | FEASIBLE
If gap >10 points and timeline <12 months: | CHALLENGING

## 02 REVERSE CALCULATION
REVERSE CALCULATION ENGINE - Target Dimension Scores
Working backwards from target to required dimension scores
INPUTS
Target Overall Health Index: | [From Goal Setting Sheet]
Total Weight: | 109
CALCULATION LOGIC
1. Overall Index = (Sum of Weighted Contributions) / Total Weight
2. Required Total Points = Target Index × Total Weight / 100
3. Allocate points based on:
- Current performance (keep strong areas stronger)
- Improvement difficulty (allocate more to easier areas)
- Strategic priority (allocate based on goals)
Dimension | Weight | Current | Target | Needed | Difficulty | Feasibility | Priority
Academic Reputation & Rigour | 10 | 75 | [TARGET SCORE] | FORMULA | 7 | [ASSESS] | [STRATEGIC]
Teacher Welfare & Development | 9 | 70 | [TARGET SCORE] | FORMULA | 6 | [ASSESS] | [STRATEGIC]
Leadership & Governance Quality | 10 | 78 | [TARGET SCORE] | FORMULA | 5 | [ASSESS] | [STRATEGIC]
Parent Engagement & SLA | 8 | 72 | [TARGET SCORE] | FORMULA | 4 | [ASSESS] | [STRATEGIC]
Student Safety & Wellness | 10 | 80 | [TARGET SCORE] | FORMULA | 6 | [ASSESS] | [STRATEGIC]
Infrastructure & Facilities | 7 | 68 | [TARGET SCORE] | FORMULA | 8 | [ASSESS] | [STRATEGIC]
Co-Curricular Education | 6 | 65 | [TARGET SCORE] | FORMULA | 5 | [ASSESS] | [STRATEGIC]
Individual Attention (PTR) | 9 | 75 | [TARGET SCORE] | FORMULA | 9 | [ASSESS] | [STRATEGIC]
Value for Money | 7 | 70 | [TARGET SCORE] | FORMULA | 7 | [ASSESS] | [STRATEGIC]
Special Needs Inclusivity | 6 | 60 | [TARGET SCORE] | FORMULA | 7 | [ASSESS] | [STRATEGIC]
Community Service & Social Responsibility | 5 | 65 | [TARGET SCORE] | FORMULA | 4 | [ASSESS] | [STRATEGIC]
Faculty Competence & Retention | 9 | 82 | [TARGET SCORE] | FORMULA | 6 | [ASSESS] | [STRATEGIC]
Internationalism & Cultural Diversity | 6 | 70 | [TARGET SCORE] | FORMULA | 7 | [ASSESS] | [STRATEGIC]
Management Vision & Growth Drive | 8 | 76 | [TARGET SCORE] | FORMULA | 4 | [ASSESS] | [STRATEGIC]
SUMMARY
Total Current Points: | FORMULA
Total Target Points: | FORMULA
Total Points to Gain: | FORMULA
Average per Dimension: | FORMULA

## 03 FEASIBILITY ANALYSIS
FEASIBILITY ANALYSIS - Achievability Assessment
Assessment Framework
Feasibility = f(Improvement Gap, Timeline, Resources, Difficulty)
Dimension | Gap | Timeline | Cost | Difficulty | Feasibility % | Risk Level | Recommendation
Academic Reputation & Rigour | CALC | 12 mo | 6 | 7 | FORMULA | [ASSESS] | [ACTION]
Teacher Welfare & Development | CALC | 6 mo | 8 | 6 | FORMULA | [ASSESS] | [ACTION]
Leadership & Governance Quality | CALC | 6 mo | 4 | 5 | FORMULA | [ASSESS] | [ACTION]
Parent Engagement & SLA | CALC | 3 mo | 3 | 4 | FORMULA | [ASSESS] | [ACTION]
Student Safety & Wellness | CALC | 9 mo | 7 | 6 | FORMULA | [ASSESS] | [ACTION]
Infrastructure & Facilities | CALC | 18 mo | 9 | 8 | FORMULA | [ASSESS] | [ACTION]
Co-Curricular Education | CALC | 6 mo | 5 | 5 | FORMULA | [ASSESS] | [ACTION]
Individual Attention (PTR) | CALC | 18 mo | 9 | 9 | FORMULA | [ASSESS] | [ACTION]
Value for Money | CALC | 12 mo | 8 | 7 | FORMULA | [ASSESS] | [ACTION]
Special Needs Inclusivity | CALC | 12 mo | 8 | 7 | FORMULA | [ASSESS] | [ACTION]
Community Service & Social Responsibility | CALC | 6 mo | 3 | 4 | FORMULA | [ASSESS] | [ACTION]
Faculty Competence & Retention | CALC | 12 mo | 7 | 6 | FORMULA | [ASSESS] | [ACTION]
Internationalism & Cultural Diversity | CALC | 12 mo | 6 | 7 | FORMULA | [ASSESS] | [ACTION]
Management Vision & Growth Drive | CALC | 6 mo | 2 | 4 | FORMULA | [ASSESS] | [ACTION]
FEASIBILITY SCALE
90-100%: Highly Feasible - Implement immediately
70-89%: Feasible - Implement with planning
50-69%: Challenging - Requires strategic focus
<50%: High Risk - Needs careful planning

## 04 ACTION MAPPING
ACTION MAPPING - Converting Targets to Specific Improvements
Detailed Action Plan by Dimension
Dimension | Target Score | Action Item | Timeline | Resources | Owner | Impact | Status
Academic Reputation & Rigour | [TARGET]
|  | Curriculum enhancement | 5 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Teacher training program | 8 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | External exam coaching | 6 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Peer school benchmarking | 2 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Academic audit | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
Teacher Welfare & Development | [TARGET]
|  | Salary increase | 1 mo | Cost 9/10 | [OWNER] | +[SCORE] | [ ]
|  | Professional development budget | 3 mo | Cost 7/10 | [OWNER] | +[SCORE] | [ ]
|  | Career progression plan | 2 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Work-life balance initiatives | 3 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Performance incentives | 4 mo | Cost 6/10 | [OWNER] | +[SCORE] | [ ]
Leadership & Governance Quality | [TARGET]
|  | Leadership training | 4 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Strategic planning workshop | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Governance restructuring | 6 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | Decision-making framework | 2 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Succession plan development | 4 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
Parent Engagement & SLA | [TARGET]
|  | Communication system upgrade | 2 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | Parent meeting schedule | 1 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Response time SLA setup | 1 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Feedback mechanism | 2 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Parent engagement programs | 3 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
Student Safety & Wellness | [TARGET]
|  | Mental health counselor | 1 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Safety audit and upgrades | 3 mo | Cost 7/10 | [OWNER] | +[SCORE] | [ ]
|  | Anti-bullying program | 4 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Wellness center setup | 6 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Staff training | 2 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
Infrastructure & Facilities | [TARGET]
|  | Technology integration | 6 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Infrastructure upgrade | 12 mo | Cost 10/10 | [OWNER] | +[SCORE] | [ ]
|  | Maintenance program | 3 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | Facilities modernization | 12 mo | Cost 9/10 | [OWNER] | +[SCORE] | [ ]
|  | Lab and library enhancement | 9 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
Co-Curricular Education | [TARGET]
|  | Sports program expansion | 4 mo | Cost 6/10 | [OWNER] | +[SCORE] | [ ]
|  | Arts program development | 4 mo | Cost 5/10 | [OWNER] | +[SCORE] | [ ]
|  | Club formation | 2 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Competition participation | 3 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | External partnerships | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
Individual Attention (PTR) | [TARGET]
|  | Class size reduction | 12 mo | Cost 10/10 | [OWNER] | +[SCORE] | [ ]
|  | Remedial program | 4 mo | Cost 6/10 | [OWNER] | +[SCORE] | [ ]
|  | Personalized learning plans | 6 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | One-on-one support hiring | 6 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Differentiation training | 3 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
Value for Money | [TARGET]
|  | Scholarship increase | 3 mo | Cost 9/10 | [OWNER] | +[SCORE] | [ ]
|  | Value communication | 2 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Fee structure review | 2 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Financial aid programs | 4 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Parent perception survey | 2 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
Special Needs Inclusivity | [TARGET]
|  | SEN coordinator hiring | 3 mo | Cost 7/10 | [OWNER] | +[SCORE] | [ ]
|  | Accessibility audit | 2 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Infrastructure accessibility | 8 mo | Cost 9/10 | [OWNER] | +[SCORE] | [ ]
|  | Staff training | 4 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | Support program setup | 6 mo | Cost 6/10 | [OWNER] | +[SCORE] | [ ]
Community Service & Social Responsibility | [TARGET]
|  | Community partnership | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Service program launch | 4 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Sustainability initiative | 6 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
|  | Student engagement drive | 2 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Environmental program | 4 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
Faculty Competence & Retention | [TARGET]
|  | Qualification upgrade support | 6 mo | Cost 6/10 | [OWNER] | +[SCORE] | [ ]
|  | Subject specialist hiring | 6 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Continuous evaluation system | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Professional development | 4 mo | Cost 5/10 | [OWNER] | +[SCORE] | [ ]
|  | Retention incentives | 6 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
Internationalism & Cultural Diversity | [TARGET]
|  | International curriculum | 8 mo | Cost 6/10 | [OWNER] | +[SCORE] | [ ]
|  | IB program | 12 mo | Cost 8/10 | [OWNER] | +[SCORE] | [ ]
|  | Partnership development | 4 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Exchange programs | 6 mo | Cost 5/10 | [OWNER] | +[SCORE] | [ ]
|  | Diversity recruitment | 4 mo | Cost 4/10 | [OWNER] | +[SCORE] | [ ]
Management Vision & Growth Drive | [TARGET]
|  | Strategic planning | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Innovation lab setup | 4 mo | Cost 3/10 | [OWNER] | +[SCORE] | [ ]
|  | Market positioning | 3 mo | Cost 2/10 | [OWNER] | +[SCORE] | [ ]
|  | Growth targeting | 2 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]
|  | Future readiness assessment | 2 mo | Cost 1/10 | [OWNER] | +[SCORE] | [ ]

## 05 RESOURCE ALLOCATION
RESOURCE ALLOCATION - Budget & Effort Planning
BUDGET ALLOCATION
Total Available Budget (₹): | [FROM GOAL SETTING]
Dimension | Priority | Cost Factor | % of Budget | Allocated (₹) | Timeline (mo) | ROI (Score) | Notes
Academic Reputation & Rigour | [SELECT] | 6 | FORMULA | FORMULA | 12 | CALC
Teacher Welfare & Development | [SELECT] | 8 | FORMULA | FORMULA | 6 | CALC
Leadership & Governance Quality | [SELECT] | 4 | FORMULA | FORMULA | 6 | CALC
Parent Engagement & SLA | [SELECT] | 3 | FORMULA | FORMULA | 3 | CALC
Student Safety & Wellness | [SELECT] | 7 | FORMULA | FORMULA | 9 | CALC
Infrastructure & Facilities | [SELECT] | 9 | FORMULA | FORMULA | 18 | CALC
Co-Curricular Education | [SELECT] | 5 | FORMULA | FORMULA | 6 | CALC
Individual Attention (PTR) | [SELECT] | 9 | FORMULA | FORMULA | 18 | CALC
Value for Money | [SELECT] | 8 | FORMULA | FORMULA | 12 | CALC
Special Needs Inclusivity | [SELECT] | 8 | FORMULA | FORMULA | 12 | CALC
Community Service & Social Responsibility | [SELECT] | 3 | FORMULA | FORMULA | 6 | CALC
Faculty Competence & Retention | [SELECT] | 7 | FORMULA | FORMULA | 12 | CALC
Internationalism & Cultural Diversity | [SELECT] | 6 | FORMULA | FORMULA | 12 | CALC
Management Vision & Growth Drive | [SELECT] | 2 | FORMULA | FORMULA | 6 | CALC
BUDGET SUMMARY
Total Allocated: | FORMULA
Remaining Buffer: | FORMULA
Budget Adequacy: | [ASSESS]

## 06 TIMELINE & MILESTONES
TIMELINE & MILESTONES - Phased Implementation Plan
Overall Timeline: | [ENTER: 12] months
PHASE BREAKDOWN
Phase 1: Foundation | Months 1-3 | Planning, assessment, small wins
Phase 2: Build | Months 4-9 | Major implementations
Phase 3: Optimize | Months 10-12 | Fine-tuning and consolidation
Milestone | Month | Target Health | Key Deliverables | Owner | Status | Approval | Notes
Kickoff | 0 | 72 | Team assembly, plan approval | [OWNER] | [ ] | [ ]
Phase 1 Review | 3 | 74 | Quick wins implemented | [OWNER] | [ ] | [ ]
Mid-Year Review | 6 | 76 | Major projects 50% done | [OWNER] | [ ] | [ ]
Phase 2 Review | 9 | 78 | Major projects complete | [OWNER] | [ ] | [ ]
Final Review | 12 | 80 | All targets achieved | [OWNER] | [ ] | [ ]

## 07 EXAMPLE SCENARIO
EXAMPLE SCENARIO - Complete Reverse Modeling Walkthrough
School: Delhi Excellence Academy ¦ Current: 72 ¦ Target: 80 ¦ Timeline: 12 months
STEP 1: GOAL SETTING
Current Health Index: 72/100 | Status: Average Performer
Target Health Index: 80/100 | Status: Strong Performer
Gap to Close: 8 points | Timeline: 12 months
Available Budget: ₹50 lakhs
STEP 2: REVERSE CALCULATION
Required Total Points: (80 × 109) / 100 = 87.2 points
Current Total Points: (72 × 109) / 100 = 78.48 points
Points to Gain: 87.2 - 78.48 = 8.72 points
DIMENSION-LEVEL TARGETS
Dimension | Current | Target | Gap | Weight | Contribution | Feasibility | Priority
D01 Academic | 75 | 80 | 5 | 10 | 0.5 | 90% | High
D02 Teacher Welfare | 70 | 78 | 8 | 9 | 0.72 | 70% | High
D03 Leadership | 78 | 82 | 4 | 10 | 0.4 | 95% | Medium
D04 Parent Engagement | 72 | 78 | 6 | 8 | 0.48 | 85% | High
D05 Safety | 80 | 85 | 5 | 10 | 0.5 | 75% | Medium
D06 Infrastructure | 68 | 75 | 7 | 7 | 0.49 | 60% | Low
D07 Co-Curricular | 65 | 72 | 7 | 6 | 0.42 | 80% | Medium
D08 Individual Attention | 75 | 80 | 5 | 9 | 0.45 | 65% | High
D09 Value for Money | 70 | 76 | 6 | 7 | 0.42 | 70% | Medium
D10 Special Needs | 60 | 68 | 8 | 6 | 0.48 | 55% | Low
D11 Community Service | 65 | 72 | 7 | 5 | 0.35 | 75% | Low
D12 Faculty Competence | 82 | 86 | 4 | 9 | 0.36 | 85% | Medium
D13 Internationalism | 70 | 76 | 6 | 6 | 0.36 | 70% | Low
D14 Management Vision | 76 | 82 | 6 | 8 | 0.48 | 90% | High
STEP 3: KEY ACTIONS
D02 - Teacher Salary Increase | 8 points | ₹25L | 6 months | HIGH
D04 - Parent SLA System | 6 points | ₹5L | 3 months | QUICK WIN
D03 - Strategic Planning | 4 points | ₹2L | 3 months | QUICK WIN
D01 - Curriculum Enhancement | 5 points | ₹8L | 9 months | HIGH
RESULT: Feasible to achieve 80/100 target in 12 months with ₹50L budget